## Invoice
Deliverable | DueDate | Status | Completion Rate
Set role title when generating payment vouchers e.g. Admin Manager | 2017-08-28 | Completed | 82.14%
On uploading invoice, the invoice should go to pending submission | 2017-08-28 | Completed
Change “add allocation” link to read as “allocate” link during allocation | 2017-08-28 | Completed
Remove Month and Year in allocation pages for invoice | 2017-08-29 | Completed
Remove breadcrumbs and use modals to view transactions | 2017-08-29 | Completed
Remove allowances captions on mobile payments statuses | 2017-08-29 | Completed
Reformat purpose of expense to follow this order “expense, for what, where, (for whom -optional)” | 2017-08-29 | Completed
New Roles Admin Manager should approve office cost similar to PM role | 2017-08-29 | Pending
Change Label from “Request New” to “Upload New” in Invoice Module | 2017-08-29 | Completed
Allow editing of allocations/invoice/LPOs | 2017-08-29 | Completed
Add Title of LPO and amount to LPO dropdown list when uploading new invoice | 2017-08-29 | Completed
Show balance of Invoice amount and auto-calculate balance and percentage when allocating in invoices and also validate inputs not to be above balance | 2017-08-30 | Completed
Restrict submitting of invoices/claims/mobile payments before allocations are complete (full amount) | 2017-08-30 | Completed
General agreement is that conflicting PM roles should be resolved by having one PM take full control due to segregation of roles e.g. Davis and Judy | 2017-08-30 | Completed
Ensure refreshing of list when submission occurs | 2017-08-30 | Completed
During Uploading New Invoice reorder supplier to be above LPO so as to filter LPOs based on supplier | 2017-08-30 | Completed
List only PIDs that current user is assigned to. | 2017-08-31 | Pending
Disable button when submitting to avoid duplicate records | 2017-08-31 | Completed
Add Supplier Name column to Invoices List | 2017-08-31 | Completed
Feature to compare variances between LPO amount and Invoice amount | TBA | Pending
Allow many-to-many relationship between LPO and invoice | TBA | Pending
On payment voucher It should state Accountant Review not approval | 2017-08-31 | Completed
Approvals should be odered according to when they were done | 2017-08-31 | Completed
History log for receipts,approvals&submissions | 2017-08-31 | Completed
Order Documents as follows LPO>Invoive document>PYmtVoucher | 2017-08-31 | Completed
Fix "413 Request Entity Too Large error" when submitting logged invoices | 2017-08-31 | Pending
Use invoice number on the invoice as REF | 2017-08-31 | Completed
Use suppliers invoice number on the payment voucher(blank if necessary) | 2017-08-31 | Completed

## LPO
Deliverable | DueDate | Status | Completion Rate
List only PIDs that current user is assigned to. | 2017-09-01 | Pending | 27.27%
Default Quotation should be selected befor allowing the user to continue to adding items | 2017-09-01 | Completed
Remove save button when allocating items | 2017-09-01 | Pending
Validate phone and email inputs when confirming supplier | 2017-09-01 | Pending
Check on redirecting when LPO is saved | 2017-09-01 | Completed
Remove breadcrumbs and use modals to view transactions | 2017-09-01 | Completed
Add Supplier Name column to LPO List | 2017-09-01 | Pending
Add Approver Signature to LPO pdf | 2017-09-01 | Pending
Allow editing of lpo, items, terms, quotations | 2017-09-01 | Pending
Disable button when submitting to avoid duplicate records | 2017-09-01 | Pending

## User
Deliverable | DueDate | Status | Completion Rate
Merge old system credentials to new system esp. password | TBA | Pending | 0%
Forgotten password not working | TBA | Pending
User profile management page | TBA | Pending
Change password page | TBA | Pending
Remove minimization button at top-right corner | TBA | Pending

## Mobile Payment
Deliverable | DueDate | Status | Completion Rate
List only PIDs that current user is assigned to. | TBA | Pending | 0%
Missing csv template download | TBA | Pending
Validate phone numbers length and structure | TBA | Pending
Show balance of payment amount and auto-calculate balance and percentage when allocating in payments and also validate inputs not to be above balance | TBA | Pending
Allow editing of allocations/payments | TBA | Pending
Attendance sheet preview | TBA | Pending
Add controls to prevent deletion of payees after they have been submitted and approved by management | TBA | Pending